## Sheet1
Shed Construction Project
Project Start Date | 2030-01-01
Task | Duration (Days) | Start Date | End Date
Project Kickoff Meeting | 1
Stakeholder Meeting | 2
Draft Blueprints | 5
Blueprint Review | 2
Purchase Materials | 1
Build Foundation | 3
Framing | 8
Finishing | 8
Construction Review | 1
Stakeholder Signoff | 1
This spreadsheet contains a simplified project schedule for a shed construction project. The tasks are listed in sequential order. Each task depends on the previous task. For example, the "Stakeholder Meeting" task cannot start until the "Project Kickoff Meeting" has finished.
The project start date is given in cell B3.
- In cell C6, create a reference to cell B3. The first task should end on the start date.
- In cell D6, create a formula that adds the duration (in days) to the start date, then subtracts one day. A tasks with a duration of one day should start in the morning and finish that afternoon, thus the start date and end date would be the same.
- In cell C7, create a formula that adds 1 day to the previous tasks' end date.
- Copy the formula inc cell C7 down the rest of the table.
- Copy the formula in cell D6 down the table.
When will the project finish?
What happens when you change the project start date?
Note that weekends are not accounted for in this spreadsheet. It is unlikely that most people want to work every weekend. What functions might help you adjust for weekends?

## Solution
Shed Construction Project
Project Start Date | 2030-01-01
Task | Duration (Days) | Start Date | End Date
Project Kickoff Meeting | 1 | 2030-01-01 | 2030-01-01
Stakeholder Meeting | 2 | 2030-01-02 | 2030-01-03
Draft Blueprints | 5 | 2030-01-04 | 2030-01-08
Blueprint Review | 2 | 2030-01-09 | 2030-01-10
Purchase Materials | 1 | 2030-01-11 | 2030-01-11
Build Foundation | 3 | 2030-01-12 | 2030-01-14
Framing | 8 | 2030-01-15 | 2030-01-22
Finishing | 8 | 2030-01-23 | 2030-01-30
Construction Review | 1 | 2030-01-31 | 2030-01-31
Stakeholder Signoff | 1 | 2030-02-01 | 2030-02-01
Formulas:
Start Date = [End Date, row above]+1
End Date = [Start Date]+[Duration (Days)]-1
This spreadsheet contains a simplified project schedule for a shed construction project. The tasks are listed in sequential order. Each task depends on the previous task. For example, the "Stakeholder Meeting" task cannot start until the "Project Kickoff Meeting" has finished.
The project start date is given in cell B3.
- In cell C6, create a reference to cell B3. The first task should end on the start date.
- In cell D6, create a formula that adds the duration (in days) to the start date, then subtracts one day. A tasks with a duration of one day should start in the morning and finish that afternoon, thus the start date and end date would be the same.
- In cell C7, create a formula that adds 1 day to the previous tasks' end date.
- Copy the formula inc cell C7 down the rest of the table.
- Copy the formula in cell D6 down the table.
When will the project finish?
What happens when you change the project start date?
Note that weekends are not accounted for in this spreadsheet. It is unlikely that most people want to work every weekend. What functions might help you adjust for weekends?

## Solution With Weekends
Shed Construction Project
Project Start Date | 2030-01-01
January / February 2030
Task | Duration (Days) | Start Date | Account for Weekends | Adjusted End Date | S | M | T | W | T | F | S
Project Kickoff Meeting | 1 | 2030-01-03 | 2030-01-03 | 2030-01-03 |  |  | 1 | 2 | 3 | 4 | 5
Stakeholder Meeting | 2 | 2030-01-04 | 2030-01-05 | 2030-01-07 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Draft Blueprints | 5 | 2030-01-08 | 2030-01-12 | 2030-01-14 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Blueprint Review | 2 | 2030-01-15 | 2030-01-16 | 2030-01-16 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Purchase Materials | 1 | 2030-01-17 | 2030-01-17 | 2030-01-17 | 27 | 28 | 29 | 30 | 31 | 1 | 2
Build Foundation | 3 | 2030-01-18 | 2030-01-20 | 2030-01-22 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Framing | 14 | 2030-01-23 | 2030-02-09 | 2030-02-11 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Finishing | 8 | 2030-02-12 | 2030-02-21 | 2030-02-21 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Construction Review | 1 | 2030-02-22 | 2030-02-22 | 2030-02-22 | 24 | 25 | 26 | 27 | 28 | 29 | 90
Stakeholder Signoff | 1 | 2030-02-25 | 2030-02-25 | 2030-02-25
Formulas:
Start Date = IF(WEEKDAY([Adjusted End Date, row above]+1)=1, [Adjusted End Date, row above]+2,IF(WEEKDAY([Adjusted End Date, row above]+1)=7,[Adjusted End Date, row above]+3,[Adjusted End Date, row above]+1))
Account for Weekends = [Start Date]+[Duration (Days)]-1+2*FLOOR.MATH([Duration (Days)]/7)
Adjusted End Date = IF(OR(WEEKDAY([Account for Weekends])=1, WEEKDAY([Account for Weekends])=7),[Account for Weekends]+2,[Account for Weekends])
Solution Description:
Column D was added. It adds the duration to the start date, subtracts 1, then adds 2 for each full week a task takes. This is done by finding the mathematical floor of the duration divided by 7, then multiplying that value by 2, then adding it to the start date.
For example, if a tasks starts on a Monday, and takes 7 days, a naive approach would indicate that the task does not fall on a weekend because the start date and end dates are on weekdays. But because the duration is 7, we know it has one weekend, so the end date should be adjusted by two. So the calculation adjusts the end date by 7/7*2.
The end date accounting for weekends is inspected. If the end date falls on a weekend, 2 days are added to the final end date. It does not matter if the proposed end date falls on a Saturday or Sunday.

## YouTube
https://www.youtube.com/watch?v=9PnNzGRAlKQ